## Project Effort Tracker
Exzelon RA Cold-Email Automation - Project Effort Tracker
FastAPI + Next.js 14 ¦ SQLite ¦ AI-Powered Lead Sourcing & Warmup
Last Updated: February 12, 2026 11:10 AM
Session # | Date(s) | Day | Session Start | Session End | Hours | Type | Key Accomplishments | Files Changed | Notes
1 | Jan 18, 2026 | Saturday | - | - | 33 | Estimated | Full system build (102 files). FastAPI backend + Next.js frontend. SQLite DB with seed data. All pipelines implemented. M365 SMTP integration. UAT verification complete. | 102 new | Initial project build.
2 | Jan 19, 2026 | Sunday | - | - | 7.5 | Estimated | Microsoft 365 SMTP config & testing. OAuth2 authentication setup. SMTP AUTH enablement. | ~5 modified | M365 config session.
3 | Jan 24, 2026 | Friday | - | - | 15 | Estimated | Bug fixes across modules. 72/72 tests passing. API endpoint corrections. Database schema refinements. | ~15 modified | Stabilization & testing.
4 | Jan 25, 2026 | Saturday | - | - | 9 | Estimated | Multi-source lead integration. Apollo adapter implementation. Pipelines dashboard UI. | ~10 modified | Feature expansion.
5 | Jan 27, 2026 | Monday | - | - | 24 | Estimated | Lead-Contact DB migration. Foreign key relationships. Data model refactoring. API endpoint updates. | ~20 modified | Major DB migration.
6 | Jan 29, 2026 | Wednesday | - | - | 6 | Estimated | Lead-Contact flow verification. End-to-end testing. Relationship integrity checks. | ~5 modified | Verification session.
7 | Feb 9-10, 2026 | Sun-Mon | - | - | 42 | Estimated | Lead sourcing optimization (13 to 629). Fixed 8 adapter bottlenecks. Warmup engine implementation. 5 new email validators. Exclusion keywords chip UI. DNS checker & blacklist monitor. | ~40 modified | Largest feature session.
8 | Feb 11-12, 2026 | Tue-Wed | 10:00 PM | Ongoing | 15 | Actual | Warmup/Mailbox management UI. Peer warmup & auto-reply system. AI content generation (Groq). Day/Phase bug fix. SOP documentation (991 lines). Project hours tracking. | ~8 modified | Current session. Time tracked.
TOTAL
Note: Sessions 1-7 hours are estimated from git commit timestamps and file activity. Session 8 onward will be tracked with actual start/end times.
Project Summary
Project Start: | January 18, 2026
Technology Stack: | FastAPI (Python) + Next.js 14 (TypeScript) + SQLite
Total Sessions: | 8
Total Hours: | ~151.5 (Sessions 1-7 estimated, Session 8+ actual)
Key Modules: | Lead Sourcing, Contact Enrichment, Email Validation, Outreach, Warmup Engine, AI Content
Deployed Tools: | Claude Code (AI pair programming)